## Utilization
Project name :Implementing 4A Camera Features
|  | October |  | Utilization in September | [9 empty] | Utilization in August | [9 empty] | Utilization in July
| Roles and Responsibilites | Utilization in % for project | Skills to develop | Week 1 | Deliverables | Week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 5 | Deliverables | Week 1 | Deliverables | Week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 5 | Deliverables | Week 1 | Deliverables | Week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 5 | Deliverables
Haranath | Camera Driver & V4L2: 1) Trying to Find Camera driver for RPI3. 2) Understanding V4L2 Driver 3) Undestanding ISP | Hands-on:60% Yocto – 60% Gerrit – 60% Learning:60% Rebrushing Other Skills:40% (C,Python,Cpp....) | 1) Camera Driver Framework 2) V4L2 Driver Framework 3)Understanding DT structure | 1)Tried to builed Yocto on RPI 2)Understanding Ycoto Internals 3)Understanding Kernel debugging | Yocto(Preparation On Yocto build ) | 1)Understanding Kernel Debugginng 2)Understanding audio framework 3)Prepared Project Desing Document 4)Ported 4.13 kernel to pi 5)Understanding kernel concepts 6)Understanding wifi driver framework 7)Undestanding slab allocator concept | RPI3 Board Bring up with 4.13 kernel | 1)1)Kernel Concepts: Kernel Synchronization Concepts 2)Successfully enbaled PI3 WiFi hotspot 3)U-boot on PI3 ported but not booting PI3 4)Make PI3 Upstream kernel image need to port 5)Done wifi controlled led blinking | Configured RPI3 WiFi Hotspot | 1)Kernel Concepts: Semaphore concepts 2)cfg80211 code base log collecting. 3)Preparing Design Document 4)Preparing for Xilinx interview | Project Design Document | 1)Attended Inetrview 2)Attended dussehra celebrations 3)Preparing Kernel Cocnepts: Semphore and Mutex 4)Understanding HAL. 5)Understanding Camera 4A resolution. | Attneded Interview | 1)Enabling Bluetooth feature in 4.12 kenrel 2)Need to change BCM2837 dts file to enbale bluetooth 3)Bluetooth Enbaled on PI3 4)Working on audio through bluetooth on PI3 5)Understanding bt internals | Enabled BT On RPI3 With BCM2837 dts file | 1)Enabled audio streaming on Bluetooth On PI3 2)Facing buffer realtd issues , need to resolve 3)Enabled audio streaming on Bluetooth On PI3 4)Script Facing issues need to resolve and gfx concept 5)Working with rakesha regarding audio streaming on bt issues 6)BT workflow understanding & preparing project docs working with mallikarjun to capture audio log as well | Enabled Audio Streaming on BT on RPI3 | 1)Document preparation & Working with Murali on DSP 2)Making New design project document according CMM level3 3)Preparing project document | New Design Document | 1)Understanding end to end flow of data from snd_bcm2835 sound card code base, need to analyse pi3 DAI code base | ALSA on RPI3 | 1)Collected log file and analysing audio flow 2))Understanding Git+Gerrit+Jenkins workflow 3)Understanding Audio Archetecture 4) 5)Prepared project document next phase for camera feature. 6))Proposed two projects based on Wifi and camera modules 7)Discussed git+gerrit+jenkins issues with satheesh and Resolved | Build & Integration using Gerrit server |  |  |  |  | Presentations at GB office | Deice Drivers Presentations at GB | 1)Ported 4.10 64bit kernel on PI3 2)Need to activate one of the feature 3)Ported 4.12 kernel on pi , trying to activate wifi on pi3 4)Porting kernel with different dts files | RPI3 Borad Bring with 4.10 kernel | 1)Getting kernel panic, need to resolve 2)Issues resolved on device tree 3)Trying porting kernel-4.12 from kernel.org on PI3 4)Getting issues while porting kerne-4.12 from kernel.org 5)Porting Issues came from kernel-4.12 from kernel.org | Getting issues porting 4.12 kernel from kernel.org So ported 4.12 kernel form PI Github
Murali Dama | 1) Android Application framework, HAL and Driver layer understanding for Camera Driver | Hands-on:70% Yocto – 20% Gerrit – 60% Learning:60% Rebrushing Other Skills:30% () | 1)Android Frame work understanding, Camera Vendor Specific HAL, V4L2 Drivers | 1) FIR and IIR Filter Basics 2) Convolution and correlation concepts understanding 3) Device Drivers basic Disucussion with Mallikarjun 4) DSP basics Training related to Pipelining, DSP requirements, Bootup Procedure with Pasha and Shravya | None | Reported at GB office for interview preparation | None | 1) Attended QCOM interview 2) Rough Draft Preparation for Camera4A fundamentals 3) Study on Wifi | Rough Draft of Camra 4A | 1) Wifi Driver Understanding 2) Document preparation for presenting on Interrupts in Linux | None | 1) Interview preparation and Attended at Bangalore Requirement: Variable Watch, Health Monitoring | None | 1) working on audio through bluetooth on PI3 2) Bluetooth Enbaled on PI3 | 1) Bluetooth Enabled. 2) Audio Steamed over Bluetooth | 1) Worked with Yasir to resolve Yocto patch apply problem. Worked with Mallikarjun to enable Bluez logs. 2)Working on Bootloaders(BBB), Helping others, Mock Interview and Git fundamentals guidance 3) Camera 4A ppt preparation for Client. 4) Enabled audio streaming on Bluetooth On PI3 | 1)Enabled Audio Steaming on Bluetooth | Preparing for interveiw. DSP fundamentals understanding and revisited previous Porting and Optimization projects. Platform Drivers Requirement: Python +DSP | Interview Preparation | Preparing for interveiw. DSP fundamentals understanding and revisited previous Porting and Optimization projects. Requirement: Python +DSP | Inrerview preparation | Preparing for interveiw at Gachibowli. Requirement: Python +DSP | Interview Preparation | With Qualcomm | NA | With Qualcomm | NA | With Qualcomm | NA | With Qualcomm | NA | Reported at Gachibowli | NA
Jignesh N Patel | 1)Preparing for Sony Interview 2). Android HAL & Camera device Driver Understanding 3). Sony 8MP IMX219 Camera driver 4). MIPI CSI-2 5). V4l2 driver | Hands-on:60% Yocto – 60% Gerrit – 60% Learning:60% Rebrushing Other Skills:40% (C,Python,Cpp....) | 1).Understanding Camera subsystem in HAL and camera device driver | 1).Understanding BCM2837 Audio Architecture 2).Attended Bluetooth Session 3). Tracing audio code flow on kernel-4.12.3 4). Trying to porting 4.13 kernel onto pi using BCM2837 dts |  | 1). Trying to enabling wifi on kernel-4.13 using bcm2837. 2). Porting and booted 4.13 kernel onto pi using BCM2837 dts. 3). Created fb and audio paches 4).Done WiFi controlled LED project on PI3(kernel-4.13 from Github) 5)We can control led through WiFI or LAN within RMS office and through LAN wihthin Votarytech premises 5).Understood ap.sh and install.sh shell script code which makes configured/enabled wlan as router 6). Created .sh script file and placed into rc.local to enable and configure WLAN as router at pi-3 boot up time. 7) Reading WLAN books for getting more info. 8). Tracing Kenrel WLAN source code. |  | 1). BeagleBone Black Board Bring Up 2).Reading WLAN books for getting more info. 3). Tracing Kenrel WLAN source code. 4) Reading WLAN books for getting more info. 5). Tracing Kenrel WLAN source code. 6). Preparing for Interview |  | 1). Preparing for secondary skills python ,shell script 2). Preparing for Qualcomm Interview |  | 1) Making Yocto build |  | 1). Enabling audio feature in 4.12 kernel 2). Need to resolve audio related issues 3). Working on audio enabling on pi3 4). need to resolve the audio issues 5). audio enabled on PI3 6). issues resolved on audio |  | 1). Anlysing DTS concept 2).Opensource and patches submitted to pi git hub 3). Facing some issues needs to resolve 4). Preparing Qcom Interview |  | 1). Preparing Qcom Interview |  | 1) Kdump Crash Analysis ,Understanding Linux ALSA, Raspberry Pi3 Audio Arch. |  | 1). Understanding Linux ALSA, Raspberry Pi3 Audio Arch. 2). 1)Audio testing done through loading diffrent audio codec driver on pi3 and removed pulseaudio library 3)Attend gerrit demo session by B&I Team 4)Attend YOCTO session 5). BCM2837 Audio code flow understanding in kernel-4.12.3. | [5 empty] | 1). Ported 4.12 64bit kernel on PI3 2). Audio testing through bluetooth on pi3 3). audio feature activating on PI 4).Need to resolve issues on audio on pi 5). |  | 1). Porting kernel with different dts files 2). Getting kernel panic, need to resolve 3). Issues resolved on device tree 4). Trying porting kernel-4.12 from kernel.org on PI3 5). Issues resolved on device tree 6). Trying porting kernel-4.12 from kernel.org on PI3 7). Kernel-4.12.2 and kernel-4.12.3 compiled 8). need to resolve the issues on bluetooth |  | 1) Kernel-4.12.2 and kernel-4.12.3 compiled 2). Ported on PI
Divya Preethika | 1.Capture Image with command line Tool 2. Capture video with camera and stream over network | Yocto – 50% Gerrit – 80% GIT – 80% Jenkins – 80% Learning:60% Board bring up – 60% (Raspberry pi 3) Ramp Up - 40% (C,Python) Linux Driver - 30% Gstreamer-50% Bluetooth-50% |  | 1)Scons session attended at gachibowli 2)Helped Gachibowli guys to interface jenkins and gerrit tools | Preparation | 1) Understanding the Bluetooth stack and revised the audio on bluetooth project 2)Practice of C and Linux | NIL | 1)Porting of 4.13 kernel on Raspberry pi3 2)Applied patches of audio and bluetooth 3)Learnt Device Driver programming basics | Porting of kernel 4.13 on raspberry pi3 | 1)Setting up of Wifi on Raspberry pi3 target board 2)Practice C 3)Helped in interfacing of gerrit and jenkins to gachibowli guys | Wifi enablement on RPI3 | 1)Building Yocto 2)Learn yocto internals 3)Yocto Build for Raspberry pi 4)To learn about plugins and stream video on Raspberry pi using Gstreamer | Yocto on RPI | 1)Learnt About Git commands 2)Setting up gitolite server 3)configured gitolite server by adding pub keys and creating repos 4)how to port kernel on Raspberry pi3 | Preparation | 1)Given permissions to users of gitolite server 2)Added source codes to the repos created 3)learnt applying patches to the kernel source code 4)Learnt about Jenkins | Gitolite Server | 1)Setting up Jenkins server 2)Configuring jenkins by creating projects 3)Enabled the email notification service when build is success or failed 4)Enabled alarm when build is success or failed | Jenkins Server | 1)Learnt about gerrit. 2)Setting up of Gerrit server 3)configured gerrit by adding users by collecting pub keys, given permissions. 4)Learnt about Bluetooth stack | Gerrit Server | 1)Interfacing of jenkins and gerrits 2)Faced many issues in interfacing 3)resolved the issues and made it work succesfully 4)When source code is reviewed in gerrit, then code is automatically built in jenkins 5)Kernel source code is also built in jenkins by writing shell script | Interfacing of Jenkins and Gerrit | At gachibowl worked on Smart Campus PoC 2)Bluetooth and BLE stacks understanding | NIL | 1)create database and Understanding MYSQL 2)Developing the application using MYSQL 3)Presentation of project and preparation of design document | Smart Campus Project | Shifted to RMS: 1)Studied about kernel concepts 2)booting process and boatloader 3)Features of Raspberry Pi3 | Preparation | 1)Learnt How to port noobs, on raspberrypi3 2)Kernel Compilation linux and building image 3)Flashing kermel image on raspberry pi3 | Porting of Kernel on RPI3 | -
ShashankArora | 1) Android Application framework, HAL, Understanding media layer (audio) | Yocto – 50% Gerrit – 30% GIT – 50% Jenkins – 30% Learning:60% Board bring up – 80% (Raspberry pi 3) Rebrushing - 20% (C,Python) Linux Driver - 30% Gstreamer-50% Bluetooth-50% | 1. Android Architecture, HAL understanding, Audio subsytem in linux, Audio interface like PCM | 1) Understand sound card, architecture, card details, audio driver flow 2) Worked on Yocto build image. | 1) worked with yasir on yocto and solved some problems | 1) Audio driver, Codec driver 2) ARM architecture and its registers 3) practiced Some linklist Question 4) different Schdeuler in linux | 1) Had discussion with malikarjun on audio driver. 2) ARM architecutre disscussion with Jignesh. 3) explained scheduler in linux | Reported to Gachibowli office for interview preparation | Had discussion of interview with Mohan | 1.Reported GB office 2. Prepared some job description related question 3) RTOS, DSP basic 4) C programming practice | Explained Question to all RMS employees | Probe() working C programming G-streamer Integration |  | 1) Enabling audio features on bcm2837. 2) Worked on DTS (Device tree source) flow 3) Solve some problems related to git. | 1) Give session on porting of kernel on BCM2837, Board-bringup, tools we need. Everything I explained to everyone. | 1) Audio Architecture 2) Analysing DTS Concepts. 3) Traced audio flow on bcm2837 Soc. 4) Found and fixed Audio bugs | 1) Give KT on DTS flow between source files 2) Delivered design document on DTS. | 1) Codec vs machine vs platform driver. 2) Audio Logs |  | On leave |  | 1) Traced snd_bcm2837 driver audio & understood internals. 2) Revised Device driver concepts. |  | 1) At GB office, done research on yocto project 2) tried to boot RPI3 and BBB using Yocto image | Successfully ported kernel image on BBB using yocto build | 1) Stuided yocto in depth. |  | 1) Ported 4.10 32bit kernel on bcm2837 SOC. 2) ported 64bit 4.12.2 kernel using bcm2710 dts file 3) Attend sessions in GB office. | 1) Delievered session on UART driver. | 1) Ported 4.12.3 64bit kernel using bcm2837 dts file 2) resolved sdhost prblem 3) resolved DTS issues | 1) Board bring-up. 2) Kernel panic debugging. | 1) replace rootfs using busybox
Rakesh Bathini | 1.Capture Image with command line Tool 2. Capture video with camera and stream over network | Yocto – 50% Gerrit – 60% GIT – 80% Jenkins – 60% Learning:60% Board bring up – 60% (Raspberry pi 3) Ramp Up - 40% (C,Python) Linux Driver - 30% Gstreamer-40% Bluetooth-40% | 1)Understand camera Module 2)Camera HAL(Hardware Abstraction Layer) 3)Gstreameri | 1)Prepared for interview 1)datastructures(single linked list,doubly linked list) 2)audio architecture discusses with mallikarjun 3)DSP basics | Interview Preparation with Respect to JD | Prepared for interview 1)multi-threaded programming,operating systems, data structures, and basic algorithms, particularly with respect to DSP platform. 3)ARM Architecture,Modes,Registers. 4)Coding with C and C++ | Interview Preparation with Respect to JD | Prepared for interview At Gachibowli Office(Head office) 1)RTOS,MULTi THREADING 2)python Multi Threading | Interview Preparation With Respect to JD | 1.Attended face to face interview at Qualcomm 2.Attended Gerrit session by satish 1.Studied about Python concepts(File operations,functions,map,filter,lambda,reduce) 2)Understanding of yocto project 3)started working on Project ( Video streaming through wifi, using Gstreamer ) 4)Trying to build custom os with youcto project 5)Reading about gstreamer | Buiding custom OS with YOCTO | 1.Debugging of gstreamer with strace 2.Colleceted logs for gstreamer and also omxplayer 3.Found some bugs on gstreamer, need to resolve that 4)Dussehra Celebrations at GB Office | 1)Playing Audio and video Using Gstreamer in x86,pi3(arm) and LAN 2)Need to Resolve Gstreamer Issues(Video Issues) | 1)Kernel Compilation, Kernel Configuration New RootFS ported on pi3 2)porting to kernel 4.12 on PI3 3)Linux Open source and working on BT 4)Understanding of DTS and DTSI files | 1)Kernel Porting 4.12 2)Cross compilation 3)Kernel Configuration | Linux Open Sourcing 1)BT modules patch analysis 2)BT facing connectivity issues need to resolve 3)Audio done resolved issues 4)working on Linux open source | Enabling Bluetooth,Audio Features on BCM2837 SOC | working on Linux opensource 1)Submitting patches to open source 2)Started working on LTP(Linux Test Project) 3)LTP Tested on X86 4)LTP tested on PI3 | 1)Submitting Patches to Kernel.org 2)Understanding LTP(linux test project) | 1)prepared Design Document for LTP 2)submitted sd host patches and Frame Buffer patches to kernel.org | 1)Submitting sdhost and frame buffer patches to Kernel.org 2)Design Document for LTP | 1)Understanding the bluez stack (protocol Rfcomm) 2)Attended gerrit+jenkins demo by sI Team 3)Attended Yocto session given by Yasir 4)start Working on Yocto | 1)Getting Practical Knowledge On Gerrit,Jenkins |  |  |  |  | Sessions: 1) BT,BLE,I2C,UART,ARM,Device Driver Basics, |  | 1)Ported 4.12 kernel on pi3 , trying to activate wifi on pi3 2)Porting kernel to 4.12,and checking for wifi drivers 3)Preparing for Qcom Interview 4)attended interview and u-boot compilation 5)Kernel-4.12.2 sdhost for bcm2837 | 1)Kernel cross compilation for arm64bit 2)Kernel Configuration 2)Preparation for Interview | 1)Kernel-4.12.2 sdhost for bcm2837 | Kernel Porting 4.12
Yasir NL | 1. Understing camera 3A and 4A feature which is provided By the Andriod 2. Undesting 3A HAL layer which is available for Andriod 3. Capture Video with Commandline on raspberry pi 3 | Yocto – 60% Gerrit – 60% GIT – 70% Jenkins – 50% Learning:60% Board bring up – 60% (Raspberry pi 3) Ramp Up - 40% (C,Python) Linux Driver - 30% Bluetooth – 40% | 1) Camera Vendor Specific HAL 2) I2C driver (understand camera interface with raspberry pi 3) | Absent first week |  | 1) Understood Yocto script Worked on Yocto with amit 2) Learned linux device drivers basics 3) Understanding the flow of LED controll over WIFI | LED blinking over wifi | 1) Making eth0 automatic During boot time(Yocto build for raspberry pi 3) 2) Yocto presentation and Hands on Training on Yocto 3) Studing internals of WIFI |  | 1) Learning charecter Device drivers 2) WIFI stack |  |  |  | 1) Yocto Build for raspberry pi 3 kernel 4.12.3 with 32- bit and 64- bit cloned from github 2) configured Yocto with local gitolite server | 1)First Yocto build with kernel 4.12.3 with 32 -bit and 64-bit 2) Yocto configure to read kernel source from local Gitolite server | 1) Applying pacths for kernel source in Yocto 2) configuring kernel and busy box 3) Modifying .b files in meta-raspberrypi 3) Worked on gerrit linking with Jenkins | 1) Made Yocto build for kernel with bcm2837.dts by applying patchs through Yocto | 1) Prepared Yocto doc 2) Building Yocto with packages like apt,gstreamer,devtools 3)Trying to make full flezed os for raspberry pi 3 using Yocto | 1) Yocto doc 2) Yocto build with packages apt,gstreamer,ssh,eth0 3) Kernel Build trough Jenkins using tool chain | 1) After Yocto build apt,eth0 and ssh where not working fixing those issues 2) eth0 and ssh issues are fixed 3) Gerrit is configured with jenkins | 1) Eithernet and ssh is working with Yocto build 2) Gerrit server link with Jenkins |  |  | woking on Smart campus Project in GB office | Smart campus project (Scanning BT and BLE device, and its RSSI value) | 1) Given presentation on BT,GIT,ARM 2) Attended presentation UART,I2C,USB 3) Helped others on GIT |  | 1) Created GITOLITE sever 2) Understing Dts 3) Understading booting soc and kernel building for target boards | 1) Understood soc booting process 2) kernel building with tool chain 3) Board bring UP of raspberry pi 3 with kernel 4.12.3(64 – bit ) | 1) maintained all source code in GITOLITE and added users for gitlolite acces 2) Startered with YOCTO build and understanding Yocto internels | 1) All source code in GITOLITE server
Swetha Huded | 1.Capture Image with commandline Tool 2. Capture video with camera and stream over network | Hands-on:50% Kernel porting-60% GIT-50% Jenkins-50% Gstreamer-50% ALSA-20% Learning:70% Ramp Up-40% (c.python,c++) Kernel concepts,Linux device drivers Bluetooth-40% Bluetooth Low Energy-70% H.264-30% |  | 1.Understanding of A2DP 2.Understanding of Gstreamer 3.understanding of H.264 4.understanding of image compression techniques 5.studied about motion estimation 6.studied about ALSA 7.understanding the flow of ALSA architecture 8.understanding ALSA driver flow | understanding of alsa architecture | 1.Understanding of Gstreamer Pipeline 2.Prepared ble for the session 3.Gave session on ble 4.Prepared document on BLE 4.Studied about Wi-Fi 5.studied about wifi working 6.kernel compilation(source from kernel.org) 7.Compiled the kernel 4.13 8.Studied about ALSA(TPS65690) | enabling wifi on rpi | 1.Study of RPI-Uboot 2.compiled uboot for raspberry pi3 64 bit 3.Analysis of ALSA driver flow 4.Study of how to enable wifi on raspberry pi 5.Went to Gacchibowli post lunch for Resume update 6.Understanding of image estimation part of (H.264) 7.understanding of WIFI 8.understanding of Gstreamer(motion estimation in H.264) | wifi streaming | 1.Studied about WIFI architecture 2.Revised c 3.studied on wifi 4.Attended Gerrit session by satish 5.studied on wifi 6.studied about regular expression in python 7.kt on gstreamer 8.worked on gstreamer to stream audio from rpi3 to lical system 9.worked on streaming video from remote location 10.able to play video without buffers on ubuntu but on raspberry pi its getting struck | video streaming using gstreamer on rpi | 1.Debugging of gstreamer with strace 2.colleceted logs for gstreamer and also omxplayer 3.found some bugs on gstreamer, need to resolve that 4.prepared for Assessment 5.Reported to Gacchibowli office 6.Dussehra Celebrations at GB Office 7.Prepared on H.264 8.Prepared on BT stack 9.Revised BLE stack | Debugging video streaming using gstreamer on rpi | 1.new rootfs ported on pi3 2.Building using different partitions 3.resolved issues on different partitions 4.enabling gstreamer on pi3 5.Gstreamer enbaling on PI3 6.workig on issues for gstreamer on pi3 7.Learning of Kernel concepts 8.studied about memory management 9.studied about os internals | audio streaming on rpi using gstreamer | 1.Written application to test gstreamer on PI3 2.Need to run application on PI board itself 3.Written application to test gstreamer on PI3 4.Need bluetooth device to test 5.Enabled audio streaming on Bluetooth On PI3 6.issues on bluez 7.Need to resolve bluez issues 8.Captured BT logs | Integration of Gstreamer with raspberry pi | 1.Understading of BT/BLE architecture 2.need to understand BT work flow 3.BEL architecure 4.Gstreamer enbaling on PI3 5.understanding of i2c protocol 6.understanding of i2c protocol | Debugging and fixing BT issues | 1.Understanding the i2c protocol 2.Understanding flow of i2c 3.studied on process management . 4.undestanding of BT logs | integration of BT with raspberry pi | 1.preparing for assessment 2.understanding process and threads Attended yocto session by yasir Updated lattest project in the resume 3.understanding A2DP 4.Issues resolved on device tree 5.kernel building usign sdhost 6.need to resolve sdhost porting | kernel porting using sdhost | [6 empty] | 1.Understanding of kernel 2.Studied about kernel internals 3.understanding of booting process of SoC 4.studied about bootloader 5.Ported 4.10 64bit kernel on PI3 | Board bring up of raspberry pi | 1.Ported 4.10 kernel on pi , trying to activate wifi on pi3 2.Ported 4.12 kernel on pi 3.audio feature activating on PI 4.Need to resolve issues on audio on pi 5.resolved modules issue and could play music using alsa 6.need to connect bluetooth wireless 7.Porting kernel with different dts files 8.Getting kernel panic, need to resolve 9.Issues resolved on device tree 10.kernel building usign sdhost 11.need to resolve sdhost porting | Porting 4.12 kernel on raspberry pi
Satheesh | Camera Driver & V4L2: 1) Trying to Find Camera driver for RPI3. 2) Understanding V4L2 Driver 3) Undestanding ISP | Other Skills:20% | 1) Camera Driver 2) V4L2 Driver | 1) Understanding V4L2 2) camera soc subsystem 3) ccd,cmos image sensors
Pradeep | Write testcases for multimedia Analysising existing tools Automation Scripts of multimedia Test cases execution and execution for Video with Camera (with help of open sources tools) | (C,Python,Cpp) | Understand Camera Subsystem in HAL Camera Driver V4L2 Driver Understanding testcases for multimedia Analysising existing tools Android cameara Stack Camera 4A document Python,C | Gone through the Project documents its dependencies Jenkins document and trying to understand Try Jenkins and Gerrit in local PC | LTP Testing + Board bring up (RP3) | Tried Jenkins and Gerrit in local PC Post lunch went to GB office for resume updation Python and C practice Took help from Satish Installation failed Holiday Python and C practice Interview Preparation Interview Preparation(Performance testing & SQL) Interview Preparation(SQL) Interview Preparation Configuring hotspot on pi3 board Interview Preparation | Test cases for Bluettoth+Tried to make pi3 as hotspot | Interview Preparation | pi3 as hotspot+wifi controlled LED + Developed shell script | Interview Preparation | LTP testing+cross compiling executable for ARM 32 and executing test cases | Worked on Blinking Led Project Dussehra Celebrations at GB Office | LTP testing+cross compiling executable for ARM 32 and executing test cases | [6 empty] | Reporting in RMS Going throught LTP document,Created Document for LTP,Practising C in Parallel Practising C and LTP document |  | Gone through C and Commands API code in LTP Work on Commands API in LTP Took help from Babu Krishna and he given some guidelines Shell Script Gone through C and Commands API code in LTP Going through Testing Concepts Spoke with Hitul, he suggested some guidelines To Learn Shell Script Read the Project Document and attended yocto session Go through gerrit and Project docs
Gopinath | -Multimedia automation using python -Test cases design and execution for images with Camera (with help of open sources tools) |  | -Need to understand the camera stack -Brush up and practice on C and Python -Understand the flow of LTP | -Understanding LTP test suites -Conditional statements in shell script -Functions in C | LTP Testing + Board bring up (RP3) | -Practicing C and Shell -Session from Shwetha about BLE -Understanding wifi and Writing testcases for it-Configuring hotspot on pi3 board -Porting latest 4.9 kernel on PI3 from kernel.org | Test cases for Bluettoth+Tried to make pi3 as hotspot | -Enabled wifi hotspot on pi3 board -Understanding of u-boot-Gone through with some linux topics -Done WiFi controlled LED project on PI3(kernel-4.13 from Github-We can controlled led through WiFI or LAN within RMS office and through LAN wihthin Votarytech premises -Understanding the project-Practicing the python -Understanding project-Regular expressions in python | pi3 as hotspot+wifi controlled LED + Developed shell script | -Understanding Wifi-RE in python -Understanding LTP -Flow of LTP-Classes in Python -Stack and queue in python-LTP project flow -Understanding mutimedia testcases-Practicing python | LTP testing+cross compiling executable for ARM 32 and executing test cases | -Session from Ishaq about Scons-Practicing python-Attended Assessment-Went GB for mock interview -Dussehra Celebrations at GB Office -Ramp up python | LTP testing+cross compiling executable for ARM 32 and executing test cases | GB |  | GB |  | On leave |  | -Gone through LTP document,Created Document for LTP -Practising C -Gone through with linux concepts -Cross compiling LTP for ARM-32 | LTP Testing + Board bring up (RP3) | -Gone through C and Linux topics -Learnt some shell script concepts and executed test suits -Prepared for the exam -Loops concept in Shell script-Attended YACTO session-Updated resume with latest project-Understanding the flow of LTP | LTP Testing + Board bring up (RP3) | GB |  | GB |  | GB |  | GB |  | GB
Shaikh Ishaque | 1)Design Document for Project. 2)understanding the control flow and architecture of linux camera system | Hands-on:55% Gerrit – 65% GIT – 70% Jenkins – 60% Learning:50% Scons:60% Board bring up – 60% (Raspberry pi 3 and Beagle Bone Black) Ramp Up - 30% (C,linux) Linux Driver - 20% | 1) Camera Driver | 3 days i worked on this weekl. 1)Understanding the project End to End and Scon Session Attended at Gachibowli. 2)Brush up the c and data structure concept |  | 1)Understanding the Scon. 2)Understand The Makefile. 3)porting the 4.13 kernel on raspberry p13 with bcm2710 dtb file succesfully done. | Board bring up (RPI3). | 1)Done WiFi controlled LED project on PI3(kernel-4.13 from Github). 2)Building the kernel 4.9 for 64bit is successfully done.wifii controleed led is done by using 4.9kernel of 32bit. | Wifii Controlled Led. Building The kernel 4.9 for 64bits. | 1)Studying the wifii and linux. 2)started working on Project ( Video streaming through wifii via Gstreamer ) 3)underatnding the Gstreamer .how to play a video via Gstareamer. 2)gstremer working through ethernet successfully play a video on pi3. | 1)Delivered the SCONS presentation. |  |  | 1)Installed the Gerrit Jenkin,Gitolite Server. 2)Understing Contineous integration Flow. |  | 1)Configure the Gerrit With Jenkin. For achieving the Contineous Integration. 2) Git command Practice | Build and integration with Gerrit Server | 1)Compiling the C code and Python Script in Jenkin. 2) compiling the kernel souce code in Jenkins. | Compile the Python Script in Jenkins | 1) Prepared The Design Document For Jenkins and Gerrit. 2)Understanding the end to end flow of the Project | Deliverd the Design Document of Gerrit and Jenkins | [8 empty] | 1)Ported 4.12 64bit kernel on PI3. 2)Board Bring up for Beagle Bone black. | Board Bringup for Beagle Bone Black | understanding the Gerrit Jenkin and Gitolite Server Reading the Document of it
Mallikarjun | 1)Preparing for Interview SONY 2)Attend SONY Interview in Banglore | Hands-on:60% Yocto – 60% Gerrit – 60% Learning:60% Rebrushing Other Skills:40% (C,Python) | 1) Camera Driver 2) V4L2 Driver 3)camera sub system | 1)understanding device driver internals 2)preparing for interview | preparing interview for qualcoom, understandig linux internalls | 1)Preparing for interview Qualcomm 2)Reporting GB Office | preparing for interview | 1)wpa_supplicant understanding 2)cfg80211 internal operation understanding | understanding wpa_supplicant configaration file, | 1)Reported at GB office 2)Attended Yocto session by Yasir 3)Understanding Yocto Project 4)Resume updation with Amith 5)Took interview for recruiting new candidates | yocto build completed | 1)Yocto bulid 2)Preparing for interview 3)Understanding HAL. 4)Understanding ALSA in Android . | preparing interview,understanding ALSA | 1)Capturing BT logs 2)Bluettoth enbaling on PI3 | Bluetooth interface understanding | 1)Capturing Audio logs 2)Faceing Issue with Audio | Audio interface understanding and enable | 1)Gstreamer enbaling on PI3 | Gstreamer enable on pi3 | 1)Understanding end to end flow of data from snd_bcm2835 sound card code base. 2)Need to find PI3 SoC uses which DAI either PCM or I2S | understanding PI3 consist audio codec or sound card | 1)Prepared organization assesment 2)Attended Gerrit session 3)Understanding Audio Archetecture 4)Audio testing on pi3 5)Attend gerrit demo session by B&I Team 6)Attend YOCTO session by Yasir 7)project details added on resume | Attend yocto session, audio architecture understanding |  |  |  |  | Presentations at GB office |  | 1)Ported 4.12 64bit kernel on PI3 | understanding PI3 architecture | 1)Porting kernel with different dts files 2)Issues resolved on device tree 3)Kernel-4.12.2 and kernel-4.12.3 compiled 5)Enabling audio feature in 4.12 kernel 6)Need to reslove | porting latest kernel on PI3, ENABLE AUDIO FEATURE

## Project Plan
Project Plan
|  |  | October | [7 empty] | November | [7 empty] | December
|  |  | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 |  | Week 1 | Deliverables | week 2 | Deliverables | Week 3 | Deliverables | Week 4 | Deliverables
| WBS | Enginners Assigned: 11 | 1)Camera driver for RPI3. 2)Undestanding ISP | Camera Driver | 1)Understanding camera drivers 2)Understanding v4l2 driver | V4l2 Driver | 1)Understanding of V4L2 2)Understanding of ALSA | V4L2 & ALSA | 1)Integration of CSI camera with RP3 2)Video capture with CSI camera and using gstreamer or other app 3)LTP testing | Camera Feature, Gstreamer Test Suite | 1)Understanding Bringing up of Dragon board & Porting and integration | Understanding of Bringing up of Dragon board | 1)Bringing up of Dragon board 2)Porting and integration | Bringing up of Dragon board | 1)Understanding of gstreamer from hardware to application (use linux apps or write Android app) 2)Yocto Skills | Gstreamer & Yocto Skills | 1)Changing v4l2 reflashing using YOCTO 2)Changing ALSA reflashing using YOCTO | Changing V4L2 & ALSA through Yocto | 1)Understanding of HAL | Android HAL Understanding | 1)Customizing HAL in RP3 and reflashing using YOCTO | Customizing HAL in RP3 and reflashing using YOCTO | 1)LTP testing 2)Customizing dragon board HAL – V4l2 | Dragon board HAL – V4l2 | Customizing dragon board HAL – ALSA | HAL-ALSA On Dragonboard
| task 1 | 1)Understanding of Camera driver for RPI3. 2)Undestanding ISP
| task 2 | 1)Understanding of Camera driver for RPI3. 2)Understanding of V4L2 driver
| task 3 | 1)Understanding of V4L2 for RPI3. 2)Understanding of ALSA driver
| task 4 | 1)Integration of CSI camera with RP3 2)Video capture with CSI camera and using gstreamer or other app
| task 5 | LTP testing
Delivery | task 6 | Camera Feature, Gstreamer Test Suite
| task 7 | 1)Understanding of Dragon Board 2)Understanding of Board Bring Up Dragon Board
| task 8 | Understanding of gstreamer from hardware to application (use linux apps or write Android app)
Delivery | task 9 | Yocto Skills
| task 10 | Changing v4l2 reflashing using YOCTO
| task 11 | Changing ALSA reflashing using YOCTO
| task 12 | Android porting on RPI3
Delivery | task 13 | Understanding of Android HAL
| task 14 | Customizing HAL in RP3 and reflashing using YOCTO
| task 15 | LTP testing
| task 16 | Customizing dragon board HAL – V4l2
| task 17 | Customizing dragon board HAL – ALSA